## Slide 1
Portfolio command view
Score movement, RAG pressure, and executive actions in one client-ready review.
Health trend
Risk pressure
Action clarity
PulsePoint AI
Monthly portfolio synthesis
Executive Portfolio Health Review
July 2026
Executive readout
The portfolio is moving improving, but 3 Red project(s) require named executive intervention before the next client checkpoint.
5
Projects
in portfolio
1/1/3
RAG Mix
green / amber / red
76%
Confidence
average data quality
Improving
Trend
portfolio movement
Top theme
Schedule slippage is affecting 3 pr...
Priority
Prioritize executive intervention f...
Data quality
76% average confidence
Deterministic scoring | Evidence-backed agent reasoning | Client-ready executive recommendations
Portfolio Health Review | July 2026

## Slide 2
Portfolio Health Snapshot
Where the portfolio stands today
Portfolio Health Review | July 2026
Chart: 
| Green | Amber | Red
Projects | 1 | 1 | 3
RAG distribution
Chart: 
| Schedule | Budget | Milestones | Blockers | Sentiment
Average score | 33 | 66.1 | 78.3 | 79.8 | 55
Average signal health
Project scoreboard
Red
Vendor Portal Recovery
24.4 score | 97% confidence
Budget burn ratio is 1.91x, above the 1.5x override threshold.
Red
Project 1
47.3 score | 51% confidence
Schedule signal is weak: Schedule variance is -61.3 percentage...
Red
Project 2
47.3 score | 40% confidence
Schedule signal is weak: Schedule variance is -58.2 percentage...
Amber
Data Migration Stabil...
67.8 score | 97% confidence
Sentiment signal is weak: Rule- based sentiment classified...
Executive implications
Insight 1
3 project(s) need executive attention.
Insight 2
2 project(s) have confidence below 70%.
Insight 3
Schedule slippage is affecting 3 project(s).

## Slide 3
Cross-Project Trends
Movement over time, not isolated project summaries
Portfolio Health Review | July 2026
Chart: 
| 18 Jun | 25 Jun | 02 Jul | 09 Jul
Average score | 53.6 | 55.9 | 57.2 | 56.7
Average portfolio score
Chart: 
| 18 Jun | 25 Jun | 02 Jul | 09 Jul
Green | 1 | 1 | 1 | 1
Amber | 0 | 1 | 1 | 1
Red | 4 | 3 | 3 | 3
RAG movement
Trend interpretation
Average health is improving, but Red concentration still requires active management.
What changed
Average portfolio score moved +3.1 points from 18 Jun to 09 Jul.

## Slide 4
Emerging Risk Themes
Patterns requiring leadership action
Portfolio Health Review | July 2026
Theme 1
Schedule slippage is affecting 3 project(s).
Theme 2
Budget pressure is affecting 1 project(s).
Risk concentration matrix
Low urgency
High urgency
Low evidence
High evidence
Each dot is a project: right = stronger evidence, higher = greater intervention need.
Top emerging risks
1
Schedule signal is weak: Schedule variance is -61.3 percentage points against expected progress.
2
Schedule signal is weak: Schedule variance is -58.2 percentage points against expected progress.
3
Sentiment signal is weak: Rule-based sentiment classified commentary as negative.
4
Budget burn ratio is 1.91x, above the 1.5x override threshold.

## Slide 5
Executive Intervention Map
Prioritize action by health score and evidence confidence
Portfolio Health Review | July 2026
Score vs. confidence
Lower score
Higher score
Higher confidence
Vendor Portal
Project 1
Project 2
Data Migration
Customer Onboarding
Intervene now
1
Vendor Portal Recovery (24.4): Reforecast remaining budget and confirm delivery scope with the project...
2
Project 1 (47.3): Review the critical path and reset near-term delivery commitments.
Watch closely
1
Data Migration Stabilization (67.8): Continue weekly monitoring and keep current governance cadence.
Protect momentum
1
Customer Onboarding Acceleration (96.9): Continue weekly monitoring and keep current governance cadence.

## Slide 6
Agent Reasoning And Evidence
What the scoring agent surfaced across plans
Portfolio Health Review | July 2026
Evidence-backed risk signals
1
Vendor Portal Recovery: Budget burn ratio is 1.91x, above the 1.5x override threshold.
2
Vendor Portal Recovery: Critical blocker open for 21 days.
3
Project 1: Schedule signal is weak: Schedule variance is -61.3 percentage points against expected progress.
Recommended management actions
1
Vendor Portal Recovery: Reforecast remaining budget and confirm delivery scope with the project owner.
2
Project 1: Review the critical path and reset near-term delivery commitments.
3
Project 2: Review the critical path and reset near-term delivery commitments.
Governance note
The agent explains why scores moved and records the reasoning trace; deterministic scoring remains the source of truth.

## Slide 7
30-Day Executive Action Plan
Client-ready decisions and next steps
Portfolio Health Review | July 2026
1
This week
Stabilize immediate delivery risk
Action 1
Prioritize executive intervention for Red projects before the next...
Action 2
Run a portfolio budget review for projects with burn rates...
Outcome: named interventions before the next checkpoint
2
Next 2 weeks
Reset commitments and owners
Action 1
Assign named owners and target resolution dates for high-...
Outcome: visible recovery path and accountable owners
3
By month end
Validate movement with evidence
Action 1
Refresh project plans, regenerate synthesis, and confirm RAG...
Outcome: refreshed RAG view ready for client governance
Scoring is deterministic and configurable. The agent explains evidence and recommendations; it does not override the score. Every deck generation is audit logged.