PulsePoint AI RAG Methodology

Transparent project-health scoring for executive delivery oversight

Purpose

PulsePoint AI converts weekly project data into a Red/Amber/Green health status that delivery leaders can trust. The status is calculated from explicit signals, weights, thresholds, and override rules; the reasoning layer explains the fixed result and recommends action.

Core Signals

| Schedule variance: Actual progress compared with expected progress from elapsed time. | Blocker severity: Open risks weighted by severity and age. |
| --- | --- |
| Budget burn ratio: Budget spent relative to delivered work. | Stakeholder sentiment: PM or client tone extracted from commentary. |
| Milestone health: Overdue milestones and near-term commitments at risk. | Scope stability: Scope churn applied as a penalty rather than a base score. |

Scoring Model

Each signal is normalized to a 0-100 sub-score, where 100 is healthiest. If optional data is missing, its weight is redistributed across available signals. Missing information lowers confidence rather than automatically punishing the project.

Composite = 0.25 Schedule + 0.25 Budget + 0.20 Milestones + 0.20 Blockers + 0.10 Sentiment + Scope Penalty

RAG Interpretation

| Status | Score | Meaning |
| --- | --- | --- |
| Green | 75-100 | On track; no material intervention required. |
| Amber | 50-74 | At risk; needs management attention this week. |
| Red | 0-49 | Off track; active intervention required. |

Override rules prevent severe risks from being hidden by averages. A critical blocker open more than 14 days or budget burn above 1.5x can force escalation.

Data Quality Rules

Fuzzy field matching handles variants such as % Complete, PercentComplete, and pct_done.

Bad rows are returned as parse warnings instead of being silently dropped.

Missing dates or budgets are treated as unknown where appropriate.

A data confidence percentage is shown beside every RAG status.

Why This Is Trustworthy

The score is reproducible from structured inputs and scoring_config.yaml. The reasoning layer cannot change the score; it can only explain it using read-only evidence. Weekly reports include sub-scores, confidence, warnings, risks, actions, and a reasoning trace.