## Summary
Field | Value
Project Name | ERP Global Rollout
Project ID | proj_amber_001
Client Name | Helio Manufacturing
Project Manager | Marcus Chen
Project Start Date | 2026-04-24
Project End Date | 2026-09-01
Budget Total | 650000
Budget Spent | 310000
Actual % Complete | 45
Schedule Slippage (d) | 8
Stakeholder Sentiment | Mixed – finance team concerned about data quality; IT sponsor supportive
Overall Status Notes | Project is recoverable but needs management attention. Data quality issues from legacy system are slowing the migration phase. One milestone is delayed. Budget is slightly over-burned at 48% spend for 45% completion. Escalation may be needed if data remediation extends beyond next sprint.

## Tasks
Task Name | Start Date | End Date | % Complete | Status | Critical Path | Notes
Requirements & Blueprint | 2026-04-24 | 2026-05-21 | 100 | completed | Yes
System Configuration | 2026-05-22 | 2026-06-26 | 90 | completed | Yes
Data Migration – Extract | 2026-06-27 | 2026-07-16 | 60 | at risk | Yes
Data Migration – Load | 2026-07-17 | 2026-08-07 | 0 | not started | Yes
Integration Testing | 2026-08-08 | 2026-08-25 | 0 | not started | Yes
Cutover & Hypercare | 2026-08-26 | 2026-09-01 | 0 | not started | Yes

## Milestones
Milestone Name | Due Date | Status | Critical Path | Notes
Blueprint Approved | 2026-05-21 | completed | Yes
Config Freeze | 2026-06-26 | completed | Yes
Mock Migration 1 | 2026-07-05 | delayed | Yes
Mock Migration 2 | 2026-07-23 | at risk | Yes
Integration Test Entry | 2026-08-08 | not started | Yes
Go-Live Readiness | 2026-09-01 | not started | Yes

## Risks
Risk / Blocker Description | Severity | Opened Date | Resolved Date | Status | Mitigation / Notes
Legacy data quality issues causing extraction rework | High | 2026-06-20 |  | open | Data cleansing team engaged; ETA +12 days
Key SME unavailability during data load phase | Medium | 2026-06-29 |  | open | Backup resource being arranged
Third-party integration vendor response time is slow | Medium | 2026-07-03 |  | open | Escalated to vendor account manager

## ScopeChanges
Scope Change Description | Change Date | Impact | Approved By | Notes
Additional legacy chart-of-accounts mapping added | 2026-06-24 | Moderate – 8 dev-days, partially absorbing buffer
New regulatory reporting requirement added by client | 2026-07-02 | Low – handled within existing sprint