## Summary
Field | Value
Project Name | Supply Chain Optimisation
Project ID | proj_amber_002
Client Name | NovaTrade Logistics
Project Manager | Priya Nair
Project Start Date | 2026-05-09
Project End Date | 2026-08-17
Budget Total | 390000
Budget Spent | 195000
Actual % Complete | 48
Schedule Slippage (d) | 5
Stakeholder Sentiment | Neutral – operations team cautious; exec sponsor supportive
Overall Status Notes | Project is under moderate pressure. Budget burn is at 50% spend against 48% completion — slightly over. One near-term milestone is at risk due to integration delays with a third-party logistics API. Team is managing but needs close monitoring.

## Tasks
Task Name | Start Date | End Date | % Complete | Status | Critical Path | Notes
Process Mapping | 2026-05-09 | 2026-05-31 | 100 | completed | No
Vendor Selection | 2026-06-01 | 2026-06-18 | 100 | completed | No
Platform Configuration | 2026-06-19 | 2026-07-13 | 75 | in progress | Yes
3PL API Integration | 2026-07-03 | 2026-07-23 | 30 | at risk | Yes
Pilot & UAT | 2026-07-24 | 2026-08-12 | 0 | not started | Yes
Rollout | 2026-08-13 | 2026-08-17 | 0 | not started | No

## Milestones
Milestone Name | Due Date | Status | Critical Path | Notes
Vendor Contract Signed | 2026-06-18 | completed | No
Config Sign-off | 2026-07-13 | on track | Yes
Integration Test Gate | 2026-07-23 | at risk | Yes
UAT Entry | 2026-07-24 | not started | Yes
Go-Live | 2026-08-17 | not started | Yes

## Risks
Risk / Blocker Description | Severity | Opened Date | Resolved Date | Status | Mitigation / Notes
3PL API credentials delayed by logistics partner | Medium | 2026-06-26 |  | open | Follow-up meeting scheduled with partner
Pilot team availability constrained during school holidays | Low | 2026-07-04 |  | open | Alternative pilot dates identified

## ScopeChanges
Scope Change Description | Change Date | Impact | Approved By | Notes
Real-time tracking dashboard added to scope | 2026-06-28 | Moderate – 5 dev-days added