## Summary
Field | Value
Project Name | Digital Transformation Initiative
Project ID | proj_green_001
Client Name | Apex Retail Group
Project Manager | Sarah Mitchell
Project Start Date | 2026-05-27
Project End Date | 2026-10-04
Budget Total | 500000
Budget Spent | 165000
Actual % Complete | 38
Schedule Slippage (d) | 0
Stakeholder Sentiment | Positive – sponsor engaged, steering committee satisfied
Overall Status Notes | Project is on track. All milestones met on time. Team morale is high, stakeholders are responsive, and blockers are resolved quickly. Budget burn is healthy at 33% spend for 38% completion.

## Tasks
Task Name | Start Date | End Date | % Complete | Status | Critical Path | Notes
Discovery & Requirements | 2026-05-27 | 2026-06-16 | 100 | completed | Yes
Architecture Design | 2026-06-17 | 2026-06-30 | 100 | completed | Yes
Dev Sprint 1 | 2026-07-01 | 2026-07-22 | 65 | in progress | Yes
Dev Sprint 2 | 2026-07-23 | 2026-08-19 | 0 | not started | No
UAT | 2026-08-20 | 2026-09-09 | 0 | not started | Yes
Training & Rollout | 2026-09-10 | 2026-10-04 | 0 | not started | No

## Milestones
Milestone Name | Due Date | Status | Critical Path | Notes
Requirements Sign-off | 2026-06-16 | completed | Yes
Architecture Approved | 2026-06-30 | completed | Yes
Sprint 1 Demo | 2026-07-22 | on track | Yes
UAT Entry Gate | 2026-08-20 | not started | Yes
Go-Live | 2026-10-04 | not started | Yes

## Risks
Risk / Blocker Description | Severity | Opened Date | Resolved Date | Status | Mitigation / Notes
Minor SME availability pressure during Sprint 2 planning | Low | 2026-07-04 |  | open | Scheduler proactively aligned SMEs
Vendor API documentation slightly delayed | Low | 2026-06-30 |  | open | Vendor confirmed delivery by next sprint

## ScopeChanges
Scope Change Description | Change Date | Impact | Approved By | Notes
Added dashboard export feature per client request | 2026-06-23 | Low – 3 dev-days added, absorbed in sprint buffer