## Summary
Field | Value
Project Name | CRM Platform Upgrade
Project ID | proj_green_002
Client Name | Solaris Financial
Project Manager | James Okonkwo
Project Start Date | 2026-06-08
Project End Date | 2026-09-06
Budget Total | 280000
Budget Spent | 72000
Actual % Complete | 32
Schedule Slippage (d) | 0
Stakeholder Sentiment | Positive – weekly updates well received
Overall Status Notes | Delivery is ahead of planned schedule by 2 days. Budget is well managed. All critical milestones on track. No blockers. Stakeholders are highly satisfied.

## Tasks
Task Name | Start Date | End Date | % Complete | Status | Critical Path | Notes
Current State Assessment | 2026-06-08 | 2026-06-20 | 100 | completed | Yes
Data Migration Mapping | 2026-06-21 | 2026-07-03 | 100 | completed | Yes
CRM Configuration | 2026-07-04 | 2026-07-28 | 55 | in progress | Yes
Integration Testing | 2026-07-29 | 2026-08-19 | 0 | not started | Yes
User Acceptance Testing | 2026-08-20 | 2026-09-01 | 0 | not started | No
Go-Live Preparation | 2026-09-02 | 2026-09-06 | 0 | not started | Yes

## Milestones
Milestone Name | Due Date | Status | Critical Path | Notes
Assessment Complete | 2026-06-20 | completed | Yes
Data Map Approved | 2026-07-03 | completed | Yes
Config Review | 2026-07-28 | on track | Yes
Integration Gate | 2026-08-19 | not started | Yes
Go-Live | 2026-09-06 | not started | Yes

## Risks
Risk / Blocker Description | Severity | Opened Date | Resolved Date | Status | Mitigation / Notes
Potential delay in test data provisioning | Low | 2026-07-05 |  | open | Test data request submitted; due in 2 days

## ScopeChanges
Scope Change Description | Change Date | Impact | Approved By | Notes