## Summary
Field | Value
Project Name | Vendor Portal Recovery Programme
Project ID | proj_red_001
Client Name | Contoso Enterprises
Project Manager | Alex Morgan
Project Start Date | 2026-04-09
Project End Date | 2026-07-28
Budget Total | 220000
Budget Spent | 198000
Actual % Complete | 50
Schedule Slippage (d) | 22
Stakeholder Sentiment | Negative – client has escalated twice; exec sponsor demanding weekly steering
Overall Status Notes | Project is in critical condition. Budget is 90% consumed with only 50% completion. Schedule has slipped 22 days. A critical blocker on third-party API credentials has been open for 25 days. Two milestones are overdue. Formal recovery plan required immediately. Escalation to executive steering committee is recommended.

## Tasks
Task Name | Start Date | End Date | % Complete | Status | Critical Path | Notes
Discovery & Scoping | 2026-04-09 | 2026-05-09 | 100 | completed | No
API Integration Design | 2026-05-10 | 2026-06-08 | 90 | at risk | Yes
Backend Development | 2026-06-09 | 2026-07-13 | 55 | blocked | Yes
Frontend Development | 2026-06-23 | 2026-07-18 | 40 | blocked | Yes
Security Review | 2026-07-14 | 2026-07-24 | 0 | not started | Yes
Deployment & Cutover | 2026-07-25 | 2026-07-28 | 0 | not started | Yes

## Milestones
Milestone Name | Due Date | Status | Critical Path | Notes
API Design Approved | 2026-06-08 | delayed | Yes
Backend Dev Complete | 2026-07-03 | at risk | Yes
Security Clearance | 2026-07-24 | at risk | Yes
Cutover Readiness | 2026-07-28 | at risk | Yes

## Risks
Risk / Blocker Description | Severity | Opened Date | Resolved Date | Status | Mitigation / Notes
Third-party API credentials not issued by vendor | Critical | 2026-06-13 |  | open | Vendor legal review blocking; legal team escalating
Security audit team backlog delaying review start | High | 2026-06-20 |  | open | Alternative audit firm being evaluated
Key backend developer on sick leave for 2 weeks | High | 2026-06-28 |  | open | Contractor being sourced urgently
Client stakeholder demanding scope extension mid-recovery | Medium | 2026-07-03 |  | open | Scope freeze discussion required in steering

## ScopeChanges
Scope Change Description | Change Date | Impact | Approved By | Notes
Vendor security review added late to project scope | 2026-06-26 | High – 10 days delay risk on critical path
Additional reporting module requested by client post-UAT | 2026-07-04 | High – 8 dev-days, no buffer remaining