## Summary
Field | Value
Project Name | Core Banking System Migration
Project ID | proj_red_002
Client Name | Meridian Bank
Project Manager | Diana Fernandez
Project Start Date | 2026-03-10
Project End Date | 2026-07-18
Budget Total | 900000
Budget Spent | 880000
Actual % Complete | 65
Schedule Slippage (d) | 35
Stakeholder Sentiment | Negative – board-level concern; CIO considering project suspension
Overall Status Notes | Project is critically over budget and severely delayed. Budget is 98% consumed with only 65% completion. Schedule has slipped 35 days from original baseline. Critical regulatory testing milestone is 3 weeks overdue. Multiple blockers including data centre access issues and regulatory sign-off delays. Immediate executive intervention required.

## Tasks
Task Name | Start Date | End Date | % Complete | Status | Critical Path | Notes
Requirements & Regulatory Mapping | 2026-03-10 | 2026-04-14 | 100 | completed | Yes
Legacy Data Extraction | 2026-04-15 | 2026-05-19 | 100 | completed | Yes
Core Banking Config | 2026-05-20 | 2026-06-28 | 85 | at risk | Yes
Regulatory UAT | 2026-06-29 | 2026-07-13 | 30 | blocked | Yes
Parallel Run | 2026-07-14 | 2026-07-18 | 0 | not started | Yes
Cutover | 2026-07-18 | 2026-07-18 | 0 | not started | Yes

## Milestones
Milestone Name | Due Date | Status | Critical Path | Notes
Data Extraction Complete | 2026-05-19 | completed | Yes
Core Config Freeze | 2026-06-28 | delayed | Yes
Regulatory UAT Sign-off | 2026-07-06 | at risk | Yes
Parallel Run Approval | 2026-07-16 | at risk | Yes
Cutover Approved | 2026-07-18 | at risk | Yes

## Risks
Risk / Blocker Description | Severity | Opened Date | Resolved Date | Status | Mitigation / Notes
Regulatory body sign-off delayed – new requirements surfaced | Critical | 2026-06-16 |  | open | Regulator liaison engaged; response expected +10d
Data centre access restrictions preventing parallel run setup | Critical | 2026-06-23 |  | open | Data centre team escalated to CTO
Core banking vendor support SLA breached twice | High | 2026-06-08 |  | open | Vendor account director on call
Staff fatigue and attrition risk after extended overtime | High | 2026-06-30 |  | open | HR reviewing retention measures
Incomplete test scripts for Parallel Run phase | Medium | 2026-07-03 |  | open | Test lead brought in to fast-track

## ScopeChanges
Scope Change Description | Change Date | Impact | Approved By | Notes
New anti-money laundering module mandated by regulator | 2026-06-13 | Critical – 3-week delay, $80k additional cost
Real-time fraud scoring integration added by client | 2026-06-20 | High – 2-week delay, $40k additional cost
Additional data archival requirements added | 2026-07-01 | Medium – 5 dev-days